## Blad1
Strokenplanning
|  | Week1:Woensdag |  |  |  | Week1:Donderdag |  |  |  | Week1:Vrijdag |  |  |  | Week2:Maandag |  |  |  | Week2:dinsdag |  |  |  | Week2:Woensdag |  |  |  | Week2:Donderdag |  |  |  | Week2:Vrijdag |  |  |  | Week3:Maandag |  |  |  | Week3:Dinsdag |  |  |  | Week3:Woensdag |  |  |  | Week3:Donderdag |  |  |  | Week3:Vrijdag
Hoofdactiviteit | Subactiviteit | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4 | blok 1 | blok 2 | blok 3 | blok 4
LeanBoard | bar: Week1:Woensdag blok 1 to Week1:Woensdag blok 2
| Teamafspraken maken | Week1:Woensdag blok 1: Iedereen
| Oriëntatie | Week1:Woensdag blok 1: Iedereen
| Doelen stellen | Week1:Woensdag blok 1: Iedereen
| Resultaten bedenken | Week1:Woensdag blok 1: Iedereen
Standaard zaken | bar: Week1:Woensdag blok 1 to Week1:Vrijdag blok 3; Week2:Maandag blok 1 to Week2:Maandag blok 3
Reflectie | bar: Week1:Woensdag blok 1; Week1:Vrijdag blok 1; Week2:Vrijdag blok 1; Week3:Vrijdag blok 1; Week3:Vrijdag blok 1; Week3:Vrijdag blok 1
Taken | bar: Week1:Woensdag blok 1
Taken verdelen op basis van functionaliteiten | bar: Week2:Maandag blok 1 to Week2:Maandag blok 2
| Plannen op basis van doelen, resultaten, succesfactoren en uitdagingen | Week1:Woensdag blok 1: Iedereen
Ontwikkelprocess
| Leanboard | Week1:Woensdag blok 1: Iedereen
| Strokenplanning | Week1:Woensdag blok 2: Quintis
| Mock-ups | Week1:Woensdag blok 1: Jesse
| storyboard | Week1:Woensdag blok 3: Hedwig
| Database design | Week1:Woensdag blok 4: Samuel
Go | bar: Week1:Woensdag blok 3
| Voorwerk presenteren | Week1:Donderdag blok 1: iedereen
| vragen voor feedback | Week1:Woensdag blok 4: Iedereen
| Alles na kijken op verbetering | Week1:Woensdag blok 4: Iedereen
Programmeren | bar: Week1:Donderdag blok 1 to Week1:Vrijdag blok 3
| Front end | Week1:Donderdag blok 2: jesse & samuel
| Back end | Week1:Donderdag blok 2: Hedwig&Quintis
| Registratie/Aanmeld scherm | Week1:Donderdag blok 3: jesse & samuel; Week2:dinsdag blok 1: Coachdag
| Dashboard | Week1:Vrijdag blok 1: Jesse; Week2:Woensdag blok 1: Jesse; Week2:Woensdag blok 2: Jesse
| Transactiescherm | Week1:Vrijdag blok 2: Samuel; Week2:Woensdag blok 1: Samuel; Week2:Woensdag blok 2: Samuel
| Budgetscherm | Week1:Vrijdag blok 1: Hedwig/Quintis
| Tabel "Users" | Week1:Vrijdag blok 2: quintis/hedwig
| Tabel "Transactions" | Week2:Woensdag blok 1: Quintis/Hedwig
| Tabel "Budgets" | Week2:Donderdag blok 1: hedwig/Quintis; Week3:Vrijdag blok 1: Allen
Allen
Trello & AVO tijd | bar: Week2:Maandag blok 1 to Week2:Maandag blok 2; Week2:dinsdag blok 1 to Week2:dinsdag blok 4
| Engels | Week1:Donderdag blok 4: Iedereen; Week1:Vrijdag blok 4: Iedereen; Week2:Maandag blok 4: Iedereen
Nederlands | bar: Week1:Donderdag blok 4; Week1:Vrijdag blok 4 to Week2:dinsdag blok 4; Week2:Woensdag blok 4
Certified Secure | bar: Week1:Donderdag blok 4; Week1:Vrijdag blok 4 to Week2:dinsdag blok 4; Week2:Woensdag blok 4
| Rekenen | Week3:Vrijdag blok 1: Allen
AYCL | bar: Week1:Donderdag blok 4; Week1:Vrijdag blok 4 to Week2:dinsdag blok 4; Week2:Woensdag blok 4; Week3:Woensdag blok 1 to Week3:Woensdag blok 3
Werk controleren | bar: Week2:Maandag blok 1 to Week2:Maandag blok 3; Week2:dinsdag blok 1 to Week2:dinsdag blok 4
Allen
Iedereen werkt eraan
Samuel
Jesse
Hedwig
Quintis
Jesse & Samuel
Hedwig & Quintis